## Product Backlog
(Describe what the project will look like when complete)
Owner | Ideal Completion Date | Project Name | Done When...
Leslie | 2020-11-23 | merge sort | there is a working file inside of the github
Tuyetlinh | 2020-11-23 | insertion sort | there is a working file inside of the github
Jacob | 2020-11-23 | quick sort | there is a working file inside of the github
Tuyetlinh, Leslie, Jacob | 2020-11-25 | bubble sort | there is a working file inside of the github
radix sort
| 2020-12-02 | figure out sequence sizes
| 2020-12-02 | types of sequences
| 2020-12-03 | look at counter for measuring algorithm efficiency
| 2020-12-04 | plot data for each algorithm's running times
| 2020-12-05 | finish SCRUM worksheet
| 2020-12-06 | make the report (linked)
| 2020-12-06 | work on the presentation (linked)

## SPRINTS - To Do
(Highlight tasks blue when finished and moved to DONE Sheet)
Sprint | Owner | Additional Team | Priority (1-10) | Project | Done When | Task #1 | Task #2 | Task #3 | Task #4 | Task #5 | Task #6 | Task #7
What week are these tasks getting done? Sprints start on Mondays. | Your Name | Anyone else who is on the team/helping | What is the weight/importance of this project? Assign tasks with Priority as well | Add project currently working on in the product backlog to this spreadsheet | Tasks are added to this sheet, marked green, and Done Statement is fulfilled from the Product Backlog | Split the project into smaller tasks and when you complete them turn them blue. You may also want to assign priority.
Sprint #1 (11/16/20) | Tuyetlinh | Jacob, Leslie (reviewed) | very important (10) | Insertion Sort | Working program (insertionSort.cpp in IDE https://ide.cs50.io/tuyetlinhnguyen/ide under "Project" folder) IDK how to upload to Github | Comment in pseudocode_+notes of algorithm | implement algorithm | compile and test for many cases to ensure successful implementation | NOTES: https://github.com/URI-CSC/212-fall-2020/blob/master/lectures/sorts.key.pdf https://www.tutorialspoint.com/data_structures_algorithms/insertion_sort_algorithm.htm https://www.tutorialspoint.com/cplusplus-program-to-implement-insertion-sort
Sprint #1 (11/16/20) | Leslie | Jacob, Tuyetlinh (reviewed) | very important (10) | MergeSort | Working program in IDE | Comment in pseudocode+notes of algorithm | implement algorithm | compile and test for many cases to ensure successful implementation
Sprint #1 (11/16/20) | Jacob | Tuyetlinh, Leslie (reviewed) | very important (10) | QuickSort | Working program in IDE | Comment in pseudocode+notes of algorithm | implement algorithm | compile and test for many cases to ensure successful implementation
Sprint #2 (11/23/20) | Tuyetlinh, Jacob, Leslie |  | very important (10) | Bubble Sort | Working program in IDE | Comment in pseudocode+notes of algorithm | implement algorithm | compile and test for many cases to ensure successful implementation
Sprint #3 (11/30/20) | Tuyetlinh | Leslie, Jacob | 10 | Presentation | set up/outlines presentation sections
Sprint #3 (11/30/20)
Sprint #3 (11/30/20)
Sprint #4 (12/7/30)
Sprint #4 (12/7/30)

## DONE
Project | Name | Done by date | Feedback | Review Code | Notes
Finished project goes here | Who is submitting the project? | Put when the project was completed | Anything of importance when you finished the project | Finalize this part of the code to make sure it works | Does it run?
Insertion sort | Tuyetlinh | 2020-11-25 | successfully implemented insertion sort & used rand() c++ function to generate random arrays of random size (see comments in cpp file) | YES (TN) YES (JZ) YES (LO) | YES
Merge sort | Leslie | 2020-11-25 | successfully implemented merge sort implemented same main as insertion sort to test | YES (LO) YES (TN) YES (JZ) | YES
Quick sort | Jacob | 2020-11-25 | successfully implemented quicksort implemented same main as insertion sort to test | YES (JZ) YES (LO) YES (TN) | YES
Bubble sort | ALL 3 | 2020-11-30 | successfully implemented bubble sort implemented same main as insertion sort to test | YES (ALL 3) | YES

## Meetings
Date | Attendees | Accomplished Tasks | Notes
2020-11-16 | Tuyetlinh, Leslie, Jacob | -Went over the rubric -discussed deadlines for the project | Collaborating on Tuyetlinh's IDE: https://ide.cs50.io/tuyetlinhnguyen/ide
2020-11-20 | Lesie, Jacob, Tuyetlinh | -end of week meeting -discuss gameplan and setting up each algorithm -deciding on which unique algorithm to choose
2020-11-30 | Tuyetlinh, Leslie, Jacob | -post-break check-in -discussed working algorithms -peer-debugged/check all sorts
2020-11-16 | Jacob | -Asking TA about project, how to use GitHUB
2020-12-03 | Jacob, Tuyetlinh | -asking TA questions | Key Points: the smaller the main file is the better; structure presentation as though you are teaching it - show how it runs - how benchmarks were performed; make one progam to run; classes are highly recommended -contain the data sets -contain the algorithms to be run
2020-12-04 | Leslie, Tuyetlinh, Jacob | -end of week meeting -talking about what we are going to do over the weekend - creating one file to run all of the code on -discussed the presentation and a tentative plan for a rehearsal

## Data Analysis
|  | Insertion Sort | Radix Sort | Mergesort | Quicksort | Bubblesort?
Sequence Type | Sequence Length | Execution Time | Execution Time
Sorted | 1 | 1e-06 | 2e-06
Sorted | 10 | 1e-06 | 2e-06
Sorted | 100 | 2e-06 | 7e-06
Sorted | 1000 | 1.6e-05 | 8.8e-05
Sorted | 10000 | 9.2e-05 | 0.001074
Sorted | 100000 | 0.000951 | 0.012901
Sorted | 1000000 | 0 | 0.15551
Reverse | 1 | 1e-06 | 0
Reverse | 10 | 1e-06 | 1e-06
Reverse | 100 | 5.2e-05 | 8e-06
Reverse | 1000 | 0.003244 | 0.000113
Reverse | 10000 | 0.32246 | 0.001245
Reverse | 100000 | 32.4076 | 0.01509
Reverse | 1000000 | 0 | 0.17663
Random | 1 | 1e-06 | 1e-06
Random | 10 | 1e-06 | 2e-06
Random | 100 | 1.7e-05 | 6e-06
Random | 1000 | 0.001512 | 5.9e-05
Random | 10000 | 0.15836 | 0.000523
Random | 100000 | 16.037 | 0.005221
Random | 1000000 | 0 | 0.05372
Partial | 1 | 1e-06 | 1e-06
Partial | 10 | 0 | 1e-06
Partial | 100 | 2e-06 | 7e-06
Partial | 1000 | 1.2e-05 | 8.9e-05
Partial | 10000 | 0.000172 | 0.001127
Partial | 100000 | 0.001081 | 0.013018
Partial | 1000000 | 0 | 0.1543